## 📊 Dashboard
Homemade Detroit — Phase 1 Tracker
Goal: 5 chef commits · 20 customer interviews · 50 waitlist signups · 14 days
PROGRESS SNAPSHOT
Chef Commits |  | Customer Interviews |  | Waitlist Signups |  | Chef Leads Sent
Target: 5 |  | Target: 20 |  | Target: 50 |  | Target: 30
WEEKLY LEARNING LOG
Week | What surprised me | What I was wrong about | Chef theme | Customer theme | Changing next week | Go/No-Go? | Notes
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
END OF WEEK 2 — GO / NO-GO CHECKLIST
Criterion | Status (✓/✗/?) | Notes
5+ chefs said 'I'd post a menu on day one'
15+ of 20 customer interviews reacted positively
Compliance pathway is clearly understood
50+ waitlist signups captured from real Detroiters
Price expectations align with $12–18/portion range

## 👨‍🍳 Chefs
Chef Pipeline
Find 30 leads → get 5 hard commits → move to Phase 2
Committed chefs
In conversation
Total leads sent
CHEF LEADS
Name | Neighborhood | What they cook | Channel | Date contacted | Last follow-up | Status | Committed? Y/N | Dishes they'd sell | Pain point | Follow-up date | Notes
Fatima A. | Hamtramck | Yemeni home cooking | Instagram DM |  |  | Lead |  | Lamb mandi, chicken saltah | No way to collect payment
Maria G. | Mexicantown | Oaxacan family recipes | In person |  |  | Lead |  | Tamales, mole negro | Doesn't know how much to cook

## 🎤 Interviews
Customer Interviews
Run 20 before drawing conclusions · Write exact words, not summaries · Signal 4–5 = strong
Interviews done
Strong signal (4–5)
Gave email
INTERVIEW LOG
Name | Neighborhood | How met | Orders/week | Food gap (exact words) | Reaction to concept | Biggest objection | Pickup or delivery? | Signal (1–5) | Price expect ($/portion) | Subscribe $9/mo? | Gave email? | Referral? | Notes
Marcus T. | Corktown | Coffee shop | 3–4x/week | Food that tastes like my grandma made it | Lit up — asked when it launches | Worried about food safety | Pickup | 5 | $14 | Y | Y | Sister in EEV | Most promising so far

## 📋 Waitlist
Waitlist Signups
Paste from Netlify Forms · Goal: 50 before Phase 2 · Keep chefs and customers separate
Total signups
Customers
Chefs
SIGNUP LOG
Name | Email | Type | Neighborhood | Date signed up | How they found us | Emailed? | Notes
BREAKDOWN BY NEIGHBORHOOD
Neighborhood | Customers | Chefs | Total
Midtown
Corktown
Mexicantown
East English Village
Hamtramck
Other

## ⚖️ Compliance
Compliance Research
Answer these questions BEFORE building · Determines your operating model
KEY QUESTIONS TO ANSWER
Question | Answer | Source | Date researched | Action needed
What does Michigan Cottage Food Law allow home chefs to sell?
What license does a home cook need to sell prepared meals in Detroit?
Are there shared commercial kitchens in Detroit chefs could use?
What's the liability picture if a customer gets sick?
Does Michigan have any food freedom bills in progress?
What are the labeling requirements for cottage food sellers?
What are the annual revenue caps under Michigan cottage food law?
Does Detroit have city-level health requirements on top of state law?
CONTACTS TO CALL
Organization | Contact / Number | What to ask | Date called | What they said
Michigan MDARD | (517) 284-5700 | What license for home cook selling prepared meals? What categories under cottage food law?
Detroit Health Dept | (313) 876-4747 | City-level requirements for home-based prepared food sales?
Wayne State Law Clinic | law.wayne.edu | Free consult — liability, operating model, terms of service
Detroit Kitchen Connect | detroitkitchenconnect.com | Shared kitchen rates, availability, chef membership options
Michigan SCORE | score.org/find-mentor | Mentor with food biz experience — compliance, unit economics
Detroit Economic Growth Corp | degc.org | Local regulatory contacts, startup support resources
SCENARIO PLANNING
Scenario | Likelihood | What it means for Homemade | Action | Status
A: Home kitchens workable with basic licensing | High | Clean unit economics. Chefs get food handler license (~$15). 80% payout intact. | Build licensing checklist into chef onboarding flow
B: Chefs need commercial kitchen for most dishes | Medium | Partner with Detroit Kitchen Connect. Group rate $15–20/hr. Adjust payout math. | Negotiate group rate before launch. Brief chefs upfront on kitchen cost.
C: Very restrictive — cottage food only to start | Low | Launch with baked goods/pantry only. Expand in Phase 2 with kitchen partnership. | Reframe Phase 1 scope. Set expectations with chef cohort.

## 📅 Schedule
14-Day Sprint Schedule
Scattered evenings + weekends · ~15–20 hrs total · Saturday is your highest-leverage day
DAY-BY-DAY PLAN
Day | Time | Tasks | Done?
WEEK 1
Monday Eve | 1.5 hrs | Set up tracking spreadsheet · Build waitlist page on Netlify · Set up Mailchimp for two lists (chefs, customers)
Tuesday Eve | 1.5 hrs | Instagram research: find 30 Detroit home chefs · Hashtags: #detroitfood #detroithomecook #mexicantowndetroit #hamtramckfood · Log each one, don't outreach yet
Wednesday Eve | 1.5 hrs | Continue research · Finish list of 30 chef leads with names, neighborhoods, what they cook, contact method
Thursday Eve | 1 hr | Send first 10 DMs · Personalize every one — name the specific dish you saw on their profile · No copy-paste
Friday Eve | 1 hr | Check DM replies · Follow up · Send 5 cold emails to chefs with catering websites or Etsy stores
SATURDAY | 5 hrs | 7–10am: Eastern Market — walk every aisle, talk to vendors, ask who cooks at home 10am–12pm: Mexicantown (Vernor Hwy) — note family-run spots, talk to anyone cooking 12–1pm: Corktown — grab food, have conversations 1–5pm: Log everything, reply to DMs, update tracker
Sunday | 2.5 hrs | Full debrief · Write 5 weekly learning bullets in Dashboard tab · Reply to any DMs · Plan Week 2 targets
WEEK 2
Monday Eve | 1 hr | 10-min DM routine · Post in Facebook groups: Detroit Foodies, Mexicantown Detroit, EEV Neighbors, Hamtramck Community — ask for customer interview volunteers
Tuesday Eve | 1.5 hrs | Follow up Week 1 DMs · Schedule calls with interested chefs · Post on Nextdoor in your neighborhood
Wednesday Eve | 1.5 hrs | Run 2 customer interviews (30 min each) · Log findings immediately in Interviews tab — exact words only
Thursday Eve | 2 hrs | Compliance deep dive · Call MDARD (517) 284-5700 · Detroit Health Dept (313) 876-4747 · Log findings in Compliance tab
Friday Eve | 1 hr | Send 10 more DMs · 5 more cold emails · Reply to all outstanding messages
SATURDAY | 5 hrs | Morning: 3–4 customer interviews at coffee shops in target neighborhoods (Corktown Coffee, Café con Leche, Germack) Afternoon: Hamtramck — Joseph Campau Ave, talk to restaurant workers 2–4pm between lunch/dinner Evening: Log everything, update all tracker tabs
Sunday | 2.5 hrs | Full debrief · Update all tabs · Run GO/NO-GO checklist in Dashboard · If 5 commits + 50 signups → move to Phase 2